## Sheet1
COLUMN | DEFINITION
PROJECT REPORT
Project | Project name.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Logged | Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Overall % Complete [E] | Percent of the project's overall (not date constrained) expected total hours that have been logged so far.
Earliest Start | The earliest start date. (Previously labeled "Start [10%]")
Start [E] | The expected start date.
Finish [10%] | The earliest finish date.
Finish [E] | The Expected [50% probability ] finish date.
Finish [90%] | The 90% probability finish date.
Finish [98%] | The 98% probability finish date.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. (Hrs Logged Billable + Hrs Remaining Billable E). Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected total non-billable hours for the selected date range (Hrs Logged Non-Billable + Hrs Remaining Non-Billable E). Non-billable status is derived from time entry & task activities.
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
$ Billable Expenses | The sum of all billable expenses for the project
$ Non-billable Expenses | The sum of all non-billable expenses for the project
$ Total Expenses | The sum of all billable and non-billable expenses for the project
$ Total Billable Cost | Dollar value of total billable hours ($ Total Billable [E]) + all billable expenses for the project, independent of date filter
$ Total Non-Billable Cost | Dollar value of total non-billable hours ($ Total Non-Billable [E]) + all non-billable expenses for the project, independent of date filter
$ Delta Contract Value vs Total Billable Cost | The amount by which the Contract Value exceeds or falls below the Total Billable Cost for the project, independent of date filter
$ Delta Contract Value vs Total Non-Billable Cost | The amount by which the Contract Value exceeds or falls below the Total Non-Billable Cost for the project, independent of date filter
$ Delta Total Billable Cost vs Total Non-Billable Cost | The amount by which the Total Billable Cost exceeds or falls below the Total Non-Billable Cost for the project, independent of date filter
Owner | The project owner.
Client | Client to which the project is associated.
Location | The parent container(s) for the project.
Reference | Reference field value from the project edit pane.
Flag | The Project's current flag, if any, will be displayed.
Is Done | Check marked if project is marked done.
Date Done | The date the project was done. Auto-populated when you mark the project folder itself done, but can be changed to a different date by the user.
On Hold | On-hold icon displayed if project is on hold.
Priority | The project's priority relative to the other projects displayed.
Deadline | The earliest deadline that applies to this Project.
Delta Deadline [90%] | The number of days by which the 90% finish date exceeds or falls below the Deadline Date.
Delay Until | The project delay date.
Work Started | Equals the date that time was first logged to any task in the project. (Previously labeled "Date Started")
Max Effort | The max hours budgeted for this project, as entered in the project's Max Effort field.
Delta Max Effort | The number of hours by which the task's overall (not date constrained) total expected hours exceeds or falls below the Max Effort.
Tags | Tags that have been added to the project.
Inherited Tags | Tags that have been added to the container(s) in which the project is nested.
Created By | The project creator.
Created On | The project created date.
Updated By | The person who made the last update to the blue project folder itself.
Updated On | The date of the last update to the blue project folder.
Date Range | The date range that you are analyzing in this report.
ID | Project ID number.
Planned Start | Date when work started, or if work has not started, it is Start [E]xpected
Contract Value | The Contract Value from the project's edit panel
$ Delta Contract vs Pay | The amount by which the Contract Value of the project exceeds or falls below the payroll dollars ($ Pay Total [E]), independent of date filter
$ Delta Contract vs Bill | The amount by which the Contract Value of the project exceeds or falls below the billable dollars ($ Total Billable [E]), independent of date filter
Task Count | The number of tasks with time logged or time remaining within the date range within the specified project(s)
Person Count | The number of people that have logged or remaining hours within the date range on a task within the specified project(s)
SUB-FOLDER REPORT
Folder | Sub-folder name.
Project | Project associated with this sub-folder.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Logged | Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Overall % Complete [E] | Percent of the Sub-folder's overall (not date constrained) expected total hours that have been logged so far.
Earliest Start | The earliest start date. (Previously labeled "Start [10%]")
Start [E] | The expected start date.
Finish [10%] | The earliest finish date.
Finish [E] | The Expected [50% probability ] finish date.
Finish [90%] | The 90% probability finish date.
Finish [98%] | The 98% probability finish date.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. (Hrs Logged Billable + Hrs Remaining Billable E). Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected total non-billable hours for the selected date range (Hrs Logged Non-Billable + Hrs Remaining Non-Billable E). Non-billable status is derived from time entry & task activities.
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
$ Billable Expenses | The sum of all billable expenses for the sub-folder regardless of filtering
$ Non-billable Expenses | The sum of all non-billable expenses for the sub-folder regardess of filtering
$ Total Expenses | The sum of all billable and non-billable expenses for the sub-folder regardless of filtering
$ Total Billable Cost | Dollar value of total billable hours
$ Total Non-Billable Cost | Dollar value of total non-billable hours
Owner | The sub-folder owner.
Client | Client to which the project is associated.
Location | The parent container(s) for the sub-folder.
Reference | Reference field value from the project edit pane.
Flag | The Sub-folders's current flag, if any, will be displayed.
Is Done | Check marked if sub-folder is marked done.
Date Done | The date the sub-folder was done. Auto-populated when you mark the sub-folder itself done, but can be changed to a different date by the user.
On Hold | On-hold icon displayed if sub-folder is on hold.
Priority | The sub-folder's priority relative to the other projects displayed.
Deadline | The earliest deadline that applies to this Sub-Folder.
Delta Deadline [90%] | The number of days by which the 90% finish date exceeds or falls below the Deadline Date.
Delay Until | The sub-folder's delay until date.
Max Effort | The max hours budgeted for this Sub-folder, as entered in the sub-folders's Max Effort field.
Delta Max Effort | The number of hours by which the sub-folder's overall (not date constrained) total expected hours exceeds or falls below the Max Effort.
Tags | Tags that have been added to the sub-folder.
Inherited Tags | Tags that have been added to the container(s) in which the project is nested.
Created By | The sub-folder creator.
Created On | The sub-folder created date.
Updated By | The person who made the last update to the sub-folder itself.
Updated On | The date of the last update to the sub-folder.
Date Range | The date range that you are analyzing in this report.
ID | Sub-folder ID number.
Project ID | Project ID number.
Planned Start | Date when work started, or if work has not started, it is Start [E]xpected
Task Count | The number of tasks with time logged or time remaining within the date range within the specified sub-folder(s)
Person Count | The number of people that have logged or remaining hours within the date range on a task within the specified sub-folder(s)
TASK REPORT
Task | Task name.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Logged | Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining[E] | Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Overall % Complete [E] | Percent of the task's overall (not date constrained) total expected hours that have been logged so far.
Earliest Start | The earliest start date. (Previously labeled "Start [10%]")
Start [E] | The expected start date.
Finish [10%] | The earliest finish date.
Finish [E] | The Expected [50% probability ] finish date.
Finish [90%] | The 90% probability finish date.
Finish [98%] | The 98% probability finish date.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. (Hrs Logged Billable + Hrs Remaining Billable E). Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected total non-billable hours for the selected date range (Hrs Logged Non-Billable + Hrs Remaining Non-Billable E). Non-billable status is derived from time entry & task activities.
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
$ Billable Expenses | The sum of all billable expenses for the task
$ Non-billable Expenses | The sum of all non-billable expenses for the task
$ Total Expenses | The sum of all billable and non-billable expenses for the task
$ Total Billable Cost | Dollar value of total billable hours ($ Total Billable [E]) + all billable expenses for the task, independent of date filter
$ Total Non-Billable Cost | Dollar value of total non-billable hours ($ Total Non-Billable [E]) + all non-billable expenses for the task, independent of date filter
$ Delta Total Billable Cost vs Total Non-Billable Cost | The amount by which the Total Billable Cost exceeds or falls below the Total Non-Billable Cost for the task, independent of date filter
Owner | The task owner.
Location | The parent container(s) for the this task.
Project | The project this task lives in.
Packaged Location | Name of the package that the task is packaged within for priority override.
Client | Client to which the task's project is associated.
Flag | The task's current flag, if any, will be displayed.
Reference | Reference field value from the task edit pane.
Is Done | Check marked if task is marked done.
Date Done | The date the task was done. Auto-populated when you mark the task done, but can be changed to a different date by the user.
On Hold | On-hold icon displayed if task is on hold.
Priority | The task's priority relative to the other tasks displayed.
Deadline | The earliest deadline that applies to this task.
Delta Deadline [90%] | The number of days by which the 90% finish date exceeds or falls below the Deadline Date.
Delay Until | The task's delay-until date.
Work Started | The date the task was started. Auto-populated when you first log time to the task, but can be changed to a different date by the user. (Previously labeled "Date Started")
Max Effort | The max hours budgeted for this task, as entered in the task's Max Effort field.
Delta Max Effort | The number of hours by which the task's overall (not date constrained) total expected hours exceeds or falls below the Max Effort.
Tags | Tags that have been added to the task.
Inherited Tags | Tags that have been added to the container(s) in which the task is nested.
Created By | The task creator.
Created On | The task created date.
Updated By | The person who made the last update to the task.
Updated On | The date of the last update to the task.
Date Range | The date range that you are analyzing in this report.
ID | Task ID number.
Planned Start | Date when work started, or if work has not started, it is Start [E]xpected
CLIENT REPORT
Client | Client name.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Logged | Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Overall % Complete [E] | Percent of the project's overall (not date constrained) expected total hours that have been logged so far.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. (Hrs Logged Billable + Hrs Remaining Billable E). Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected Total non-billable hours for the selected date range. (Hrs Logged Non-Billable + Hrs Remaining Non-Billable. Non-billable status is derived from the task activity.
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
$ Billable Expenses | The sum of the billable expenses for all of the specified client's projects
$ Non-billable Expenses | The sum of the non-billable expenses for all of the specified client's projects
$ Total Expenses | The sum of the billable and non-billable expenses for all of the specified client's projects
$ Total Billable Cost | Dollar value of total billable hours ($ Total Billable [E]) + all billable expenses for all the specified client's projects, independent of date filter
$ Total Non-Billable Cost | Dollar value of total non-billable hours ($ Total Non-Billable [E]) + all non-billable expenses for all the specified client's projects, independent of date filter
$ Delta Contract Value vs Total Billable Cost | The amount by which the Contract Value of the client exceeds or falls below the Total Billable Cost for all the specified client's projects, independent of date filter
$ Delta Contract Value vs Total Non-Billable Cost | The amount by which the Contract Value of the client exceeds or falls below the Total Non-Billable Cost for all the specified client's projects, independent of date filter
$ Delta Total Billable Cost vs Total Non-Billable Cost | The amount by which the Total Billable Cost exceeds or falls below the Total Non-Billable Cost for all the specified client's projects, independent of date filter
Earliest Start | The earliest start date. (Previously labeled "Start [10%]")
Start [E] | The expected start date.
Finish [10%] | The earliest finish date.
Finish [E] | The Expected [50% probability ] finish date.
Finish [90%] | The 90% probability finish date.
Finish [98%] | The 98% probability finish date.
Owner | The client owner.
Reference | Reference field value from the client edit pane.
Flag | The client's current flag, if any, will be displayed.
Is Done | Check marked if client is marked done.
Date Done | The date the client was done. Auto-populated when you mark the client itself done, but can be changed to a different date by the user.
Created By | The client creator.
Created On | The client created date.
Updated By | The person who made the last update to the client itself.
Updated On | The date of the last update to the client itself.
Date Range | The date range that you are analyzing in this report.
ID | Client ID number.
Contract Value | The Contract Value from the Client's edit panel
$ Delta Contract vs Pay | The amount by which the Contract Value of the client exceeds or falls below the payroll dollars ($ Pay Total [E]), independent of date filter
$ Delta Contract vs Bill | The amount by which the Contract Value of the client exceeds or falls below the billable dollars ($ Total Billable [E]), independent of date filter
Planned Start | Date when work started, or if work has not started, it is Start [E]xpected
Task Count | The number of tasks with time logged or time remaining within the date range for the specified client(s)
Project Count | The number of projects with time logged or time remaining within the date range for the specified client(s)
PERSON REPORT
Person | Workspace member name.
Team | The person's team association.
External ID | The person's external ID as entered in the member profile.
Hrs Available | Hours that the person has available and unscheduled between now and the end of the selected date range.
Workload | The total of Hrs logged + Hrs unlogged + Hrs Remaining E + Hrs Available during the selected date range.
Hrs Unlogged | Hours that the person had available between the beginning of the selected date range and now, minus Hrs Logged during that period.
Hrs Logged | Hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected scheduled hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. (Hrs Logged Billable + Hrs Remaining Billable E). Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected total non-billable hours for the selected date range. (Hrs Logged Non-Billable + Hrs Remaining Non-Billable E). Billable status is derived from time entry & task activities.
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
Date Range | The date range that you are analyzing in this report.
ID | The person ID number.
Total Availability | The person's total hours of availability for the selected date range, based on the person's availability setting.
Task Count | The number of tasks with time remaining assigned to the member, or to which a member has logged time within the date range
Project Count | The number of projects containing tasks with time remaining assigned to the member, or to which a member has logged time within the date range
TEAM REPORT
Team | Team name.
Hrs Available | Hours that the team has available and unscheduled between now and the end of the selected date range.
Workload | The total of Hrs logged + Hrs unlogged + Hrs Remaining E + Hrs Available during the selected date range.
Hrs Unlogged | Hours that the team had available between the beginning of the selected date range and now, minus Hrs Logged during that period.
Hrs Logged | Hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected scheduled hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. (Hrs Logged Billable + Hrs Remaining Billable E). Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected total non-billable hours for the selected date range. (Hrs Logged Non-Billable + Hrs Remaining Non-Billable E). Billable status is derived from time entry & task activities.
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
Date Range | The date range that you are analyzing in this report.
ID | Team ID number.
Total Availability | The team's total hours of availability for the selected date range, based on the members' availability settings.
Task Count | The number of tasks with time remaining assigned to members of the team, or to which team members have logged time within the date range
Project Count | The number of projects containing tasks with time remaining assigned to members of the team, or to which team members have logged time within the date range
ACTIVITY REPORT
Activity | Activity name.
Billable | An X indicates that this is a billable activity.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Logged | Total hours already logged between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected hours remaining between now and the end of the selected date range.
Hrs Total Billable [E] | Expected total billable hours during the selected date range. Relevant for billable activities only.
Hrs Total Non-Billable [E] | Expected total non-billable hours during the selected date range. Relevant for non-billable activities only.
Hrs Logged Billable | Billable Hours already logged between the beginning of the selected date range and now. Relevant for billable activities only.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Relevant for non-billable activities only.
Hrs Remaining Billable[E] | Billable hours remaining between now and the end of the selected date range and now. Relevant for billable activities only.
Hrs Remaining Non-Billable [E] | Non-billable hours remaining between now and the end of the selected date range and now. Relevant for non-billable activities only.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
Date Range | The date range that you are analyzing in this report.
ID | Activity ID Number.
Person Count | The number of people with time logged or time remaining associated to the activity within the date range
Task Count | The number of tasks with time logged or remaining associated to the activity within the date range
Project Count | The number of projects containing tasks with time logged or remaining associated to the activity within the date range
CUSTOM FIELD REPORT
Custom Field | Custom field name.
Hrs Total [E] | Expected total hours (Hrs Logged + Hrs Remaining E) during the selected date range.
Hrs Logged | Hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) between the beginning of the selected date range and now.
Hrs Remaining [E] | Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) between now and the end of the selected date range.
Hrs Total Billable [E] | Expected total billable hours for the selected date range. Billable status is derived from time entry & task activities.
Hrs Total Non-Billable [E] | Expected total non-billable hours for the selected date range. Non-billable status is derived from time entry & task activities
Hrs Logged Billable | Billable hours already logged between the beginning of the selected date range and now. Billable status is derived from time entry activities.
Hrs Logged Non-Billable | Non-billable hours already logged between the beginning of the selected date range and now. Non-billable status is derived from time entry activities.
Hrs Remaining Billable [E] | Expected remaining billable hours between now and the end of the selected date range. Billable status is derived from task activities.
Hrs Remaining Non-Billable [E] | Expected remaining non-billable hours between now and the end of the selected date range. Non-billable status is derived from task activities.
$ Total Billable [E] | Dollar value of expected billable hours (Hrs Total Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Total Non-Billable [E] | Dollar value of expected non-billable hours (Hrs Total Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Billable | Dollar value of billable hours already logged (Hrs Logged Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Logged Non-Billable | Dollar value of non-billable hours already logged (Hrs Logged Non-Billable ) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Billable [E] | Dollar value of remaining billable hours (Hrs Remaining Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Remaining Non-Billable [E] | Dollar value of remaining non-billable hours (Hrs Remaining Non-Billable [E]) in the selected date range. Dollar value is derived from your rate sheet and labeled to reflect your workspace currency.
$ Pay Total [E] | Dollar value of payroll for total expected hours (Hrs Total [E] ) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Logged | Dollar value of payroll for hours already logged (Hrs Logged) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Pay Remaining [E] | Dollar value of payroll for remaining hours (Hrs Remaining [E]) in the selected date range. Dollar value is derived from your pay rate sheet and labeled to reflect your workspace currency.
$ Delta Bill vs. Pay | The amount by which billable dollars ($ Total Billable [E]) exceeds or falls below payroll dollars ($ Pay Total [E]).
$ Billable Expenses | The sum of the billable expenses for all items with a specified custom field value
$ Non-Billable Expenses | The sum of the non-billable expenses for all items with a specificed custom field value
$ Total Expenses | The sum of the billable and non-billable expenses for all items with a specified custom field value
$ Total Billable Cost | Dollar value of total billable hours ($ Total Billable [E]) + all billable expenses for all items with a specified custom field value, independent of date filter
$ Total Non-Billable Cost | Dollar value of total non-billable hours ($ Total Non-Billable [E]) + all non-billable expenses for all items with a specified custom field value, independent of date filter
$ Delta Contract vs Total Billable Cost | The amount by which the Contract Values of projects exceeds or falls below the Total Billable Cost for all items with a specified custom field value, independent of date filter
$ Delta Contract vs Total Non-Billable Cost | The amount by which the Contract Values of projects exceeds or falls below the Total Non-Billable Cost for all items with a specified custom field value, independent of date filter
$ Delta Total Billable Cost vs Total Non-Billable Cost | The amount by which the Total Billable Cost exceeds or falls below the Total Non-Billable Cost for all items with a specified custom field value, independent of date filter
Date Range | The date range that you are analyzing in this report.
ID | Custom Field ID Number.
Person Count for Task Custom Fields | The number of people that have logged or remaining hours within the date range on a task with a specified custom task field value
Task Count for Task Custom Fields | The number of tasks with logged or remaining hours within the date range on a task with a specified custom task field value
Project Count for Task Custom Fields | The number of projects containing tasks with logged or remaining hours within the date range on a task with a specified custom task field value
Person Count for Project Custom Fields | The number of people that have logged or remaining hours within the date range on a task that is within a project with a specified custom project field value
Task Count for Project Custom Fields | The number of tasks within a project with a specified custom project field value that have logged or remaining hours within the date range
Project Count for Project Custom Fields | The number of projects with a specified custom field value containing tasks that have logged or remaining hours within the date range
Contract Value | The sum of Contract Values for projects with a specified custom field value
PROJECT BASELINE REPORT
Project | Project name.
Owner | The project owner.
Client | Client to which the project is associated.
Location | The parent container(s) for the project.
Tags | Tags that have been added to the project
Inherited Tags | Tags that have been added to the container(s) in which the project is nested.
Reference | Reference field value from the project edit pane.
Flag | The Project's current flag, if any, will be displayed.
Priority | The project's priority relative to the other projects displayed.
Work Started | Equals the date that time was first logged to any task in the project.
Date Done | The date the project was done. Auto-populated when you mark the project folder itself done, but can be changed to a different date by the user.
D: Finish [E] | Delta: The difference in Expected finish dates, between the baseline and current date, measured in days.
B: Finish [E] | Baseline: The Expected [50% probability ] finish date as of your baseline date.
C: Finish [E] | Current: The Expected [50% probability ] finish date as of the current date.
D: Hrs Total [E] | Delta: The difference in Expected total hours, between the baseline and current date.
B: Hrs Total [E] | Baseline: Expected total hours (Hrs Logged + Hrs Remaining E) as of your baseline date.
C: Hrs Total [E] | Current: Expected total hours (Hrs Logged + Hrs Remaining E) as of your baseline date.
D: Hrs Logged | Delta: The difference in hours logged between the baseline and current date.
B: Hrs Logged | Baseline: Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) as of your baseline date.
C: Hrs Logged | Current: Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) as of the current date.
D: Hrs Remaining [E] | Delta: The difference in Expected hours remaining between the baseline and current date.
B: Hrs Remaining [E] | Baseline: Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) as of your baseline date.
C: Hrs Remaining [E] | Current: Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) as of the current date.
D: Earliest Start | Delta: The difference in the earliest start date, between the baseline and current date, measured in days.
B: Earliest Start | Baseline: The earliest start date as of your baseline date.
C: Earliest Start | Current: The earliest start dateas of the current date.
D: Start [E] | Delta: The difference in the expected start date, between the baseline and current date, measured in days.
B: Start [E] | Baseline: The expected start date, as of your baseline date.
C: Start [E] | Current: The expected start date, as of the current date.
D: Finish [10%] | Delta: The difference in the earliest finish date, between the baseline and current date, measured in days.
B: Finish [10%] | Baseline: The earliest finish date, as of your baseline date.
C: Finish [10%] | Current: The earliest finish date, as of the current date.
D: Finish [90%] | Delta: The difference between 90% probability finish date, between the baseline and current date, measured in days.
B: Finish [90%] | Baseline: The 90% probability finish date, as of your baseline date.
C: Finish [90%] | Current: The 90% probability finish date, as of the current date.
D: Planned Start | Delta: The difference between the Planned Start date of the project, between the baseline and current date, measured in days.
B: Planned Start | Baseline: Date when work started, or if work has not started, Start [E]xpected, as of your baseline date.
C: Planned Start | Current: Date when work started, or if work has not started, Start [E]xpected, as of the current date.
D: Deadline | Delta: The difference in the project deadline, between the baseline and current date, measured in days.
B: Deadline | Baseline: The project deadline date, as of your baseline date.
C: Deadline | Current: The project deadline date, as of the current date.
D: Delay Until | Delta: The difference in the project delay date, between the baseline and current date, measured in days.
B: Delay Until | Baseline: The project delay date, as of your baseline date.
C: Delay Until | Current: The project delay date, as of the current date.
B: Is Done | Baseline: Check marked if project is marked done as of the baseline date.
C: Is Done | Current: Check marked if project is marked done as of the current date.
B: On Hold | Baseline: On-hold icon displayed if project is on hold as of the baseline date.
C: On Hold | Current: On-hold icon displayed if project is on hold as of the current date.
B: Overall % Complete [E] | Baseline: Percent of the task's overall (not date constrained) expected total hours that have been logged so far, as of the baseline date.
C: Overall % Complete [E] | Current: Percent of the task's overall (not date constrained) expected total hours that have been logged so far, as of the current date.
D: Max Effort | Delta: The difference in max hours budgeted for this project between the baseline and current date.
B: Max Effort | Baseline: The max hours budgeted for this project, as entered in the project's Max Effort field, as of the baseline date.
C: Max Effort | Current: The max hours budgeted for this project, as entered in the project's Max Effort field, as of the current date.
Date Range | Baseline date and current date are the "range".
Created By | The project creator.
Created On | The project created date.
Updated By | The person who made the last update to the blue project folder itself.
Updated On | The date of the last update to the blue project folder.
ID | Project ID number.
TASK BASELINE REPORT
Task | Task name.
Project | Project name.
Location | The parent container(s) for the this task.
Packaged Location | Name of the package that the task is packaged within for priority override.
Owner | The task owner.
Client | Client to which the project is associated.
Tags | Tags that have been added to the task
Inherited Tags | Tags that have been added to the container(s) in which the task is nested.
Reference | Reference field value from the task edit pane.
Flag | The task's current flag, if any, will be displayed.
Priority | The task's priority relative to the other tasks displayed.
Work Started | Equals the date that time was first logged to any task.
Date Done | The date the task was done. Auto-populated when you mark the task done, but can be changed to a different date by the user.
D: Finish [E] | Delta: The difference in Expected finish dates, between the baseline and current date, measured in days.
B: Finish [E] | Baseline: The Expected [50% probability ] finish date as of your baseline date.
C: Finish [E] | Current: The Expected [50% probability ] finish date as of the current date.
D: Hrs Total [E] | Delta: The difference in Expected total hours, between the baseline and current date.
B: Hrs Total [E] | Baseline: Expected total hours (Hrs Logged + Hrs Remaining E) as of your baseline date.
C: Hrs Total [E] | Current: Expected total hours (Hrs Logged + Hrs Remaining E) as of your baseline date.
D: Hrs Logged | Delta: The difference in hours logged, between the baseline and current date.
B: Hrs Logged | Baseline: Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) as of your baseline date.
C: Hrs Logged | Current: Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) as of the current date.
D: Hrs Remaining [E] | Delta: The difference in Expected hours, between the baseline and current date.
B: Hrs Remaining [E] | Baseline: Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) as of your baseline date.
C: Hrs Remaining [E] | Current: Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) as of the current date.
D: Earliest Start | Delta: The difference in the earliest start date, between the baseline and current date, measured in days.
B: Earliest Start | Baseline: The earliest start date as of your baseline date.
C: Earliest Start | Current: The earliest start dateas of the current date.
D: Start [E] | Delta: The difference in the expected start date, between the baseline and current date, measured in days.
B: Start [E] | Baseline: The expected start date, as of your baseline date.
C: Start [E] | Current: The expected start date, as of the current date.
D: Finish [10%] | Delta: The difference in the earliest finish date, between the baseline and current date, measured in days.
B: Finish [10%] | Baseline: The earliest finish date, as of your baseline date.
C: Finish [10%] | Current: The earliest finish date, as of the date.
D: Finish [90%] | Delta: The 90% probability finish date, between the baseline and current date, measured in days.
B: Finish [90%] | Baseline: The 90% probability finish date, as of your baseline date.
C: Finish [90%] | Current: The 90% probability finish date, as of the current date.
D: Planned Start | Delta: The difference between the Planned Start date of the task, between the baseline and current date, measured in days.
B: Planned Start | Baseline: Date when work started, or if work has not started, Start [E]xpected, as of your baseline date.
C: Planned Start | Current: Date when work started, or if work has not started, Start [E]xpected, as of the current date.
D: Deadline | Delta: The difference in the project deadline, between the baseline and current date, measured in days.
B: Deadline | Baseline: The project deadline date, as of your baseline date.
C: Deadline | Current: The project deadline date, as of the current date.
D: Delay Until | Delta: The difference in the task delay date, between the baseline and current date, measured in days.
B: Delay Until | Baseline: The task delay date, as of your baseline date.
C: Delay Until | Current: The task delay date, as of the current date.
B: Is Done | Baseline: Check marked if task is marked done as of the baseline date.
C: Is Done | Current: Check marked if task is marked done as of the current date.
B: On Hold | Baseline: On-hold icon displayed if task is on hold as of the baseline date.
C: On Hold | Current: On-hold icon displayed if task is on hold as of the current date.
B: Overall % Complete [E] | Baseline: Percent of the task's overall (not date constrained) expected total hours that have been logged so far, as of the baseline date.
C: Overall % Complete [E] | Current: Percent of the task's overall (not date constrained) expected total hours that have been logged so far, as of the current date.
D: Max Effort | Delta: The difference in max hours budgeted for this task between the baseline and current date.
B: Max Effort | Baseline: The max hours budgeted for this task, as entered in the task's Max Effort field, as of the baseline date.
C: Max Effort | Current: The max hours budgeted for this task, as entered in the task's Max Effort field, as of the current date.
Date Range | Baseline date and current date are the "range".
Created By | The task creator.
Created On | The task created date.
Updated By | The person who made the last update to the task.
Update On | The date of the last update to the task.
ID | Task ID number.
CLIENT BASELINE REPORT
Client | Client name.
Owner | The client owner.
Reference | Reference field value from the client edit pane.
Flag | The client's current flag, if any, will be displayed.
Date Done | The date the client was done. Auto-populated when you mark the client done, but can be changed to a different date by the user.
D: Finish [E] | Delta: The difference in Expected finish dates, between the baseline and current date, measured in days.
B: Finish [E] | Baseline: The Expected [50% probability ] finish date as of your baseline date.
C: Finish [E] | Current: The Expected [50% probability ] finish date as of the current date.
D: Hrs Total [E] | Delta: The difference in Expected total hours, between the baseline and current date.
B: Hrs Total [E] | Baseline: Expected total hours (Hrs Logged + Hrs Remaining E) as of your baseline date.
C: Hrs Total [E] | Current: Expected total hours (Hrs Logged + Hrs Remaining E) as of your baseline date.
D: Hrs Logged | Delta: The difference in hours logged, between the baseline and current date.
B: Hrs Logged | Baseline: Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) as of your baseline date.
C: Hrs Logged | Current: Total hours already logged (Hrs Logged Billable + Hrs Logged Non-Billable) as of the current date.
D: Hrs Remaining [E] | Delta: The difference in Expected hours, between the baseline and current date.
B: Hrs Remaining [E] | Baseline: Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) as of your baseline date.
C: Hrs Remaining [E] | Current: Expected hours (Hrs Remaining Billable E + Hrs Remaining Non-Billable E) as of the current date.
D: Earliest Start | Delta: The difference in the earliest start date, between the baseline and current date, measured in days.
B: Earliest Start | Baseline: The earliest start date as of your baseline date.
C: Earliest Start | Current: The earliest start dateas of the current date.
D: Start [E] | Delta: The difference in the expected start date, between the baseline and current date, measured in days.
B: Start [E] | Baseline: The expected start date, as of your baseline date.
C: Start [E] | Current: The expected start date, as of the current date.
D: Finish [10%] | Delta: The difference in the earliest finish date, between the baseline and current date, measured in days.
B: Finish [10%] | Baseline: The earliest finish date, as of your baseline date.
C: Finish [10%] | Current: The earliest finish date, as of the date.
D: Finish [90%] | Delta: The 90% probability finish date, between the baseline and current date, measured in days.
B: Finish [90%] | Baseline: The 90% probability finish date, as of your baseline date.
C: Finish [90%] | Current: The 90% probability finish date, as of the current date.
D: Planned Start | Delta: The difference between the Planned Start date of the task, between the baseline and current date, measured in days.
B: Planned Start | Baseline: Date when work started, or if work has not started, Start [E]xpected, as of your baseline date.
C: Planned Start | Current: Date when work started, or if work has not started, Start [E]xpected, as of the current date.
D: Deadline | Delta: The difference in the project deadline, between the baseline and current date, measured in days.
B: Deadline | Baseline: The project deadline date, as of your baseline date.
C: Deadline | Current: The project deadline date, as of the current date.
D: Delay Until | Delta: The difference in the task delay date, between the baseline and current date, measured in days.
B: Delay Until | Baseline: The task delay date, as of your baseline date.
C: Delay Until | Current: The task delay date, as of the current date.
B: Is Done | Baseline: Check marked if task is marked done as of the baseline date.
C: Is Done | Current: Check marked if task is marked done as of the current date.
B: On Hold | Baseline: On-hold icon displayed if project is on hold as of the baseline date.
C: On Hold | Current: On-hold icon displayed if project is on hold as of the current date.
B: Overall % Complete [E] | Baseline: Percent of the task's overall (not date constrained) expected total hours that have been logged so far, as of the baseline date.
C: Overall % Complete [E] | Current: Percent of the task's overall (not date constrained) expected total hours that have been logged so far, as of the current date.
D: Max Effort | Delta: The difference in max hours budgeted for this project between the baseline and current date.
B: Max Effort | Baseline: The max hours budgeted for this project, as entered in the task's Max Effort field, as of the baseline date.
C: Max Effort | Current: The max hours budgeted for this project, as entered in the task's Max Effort field, as of the current date.
Date Range | Baseline date and current date are the "range".
Created By | The client creator.
Created On | The client created date.
Updated By | The person who made the last update to the client itself.
Update On | The date of the last update to the client itself.
ID | Client ID number.